## Gantt Chart
PROJECT TITLE: CGB-SIS |  |  |  | COMPANY NAME | [6 empty] | CGB-SIS
PROJECT MANAGER: CHRISTIAN GREG BOLASTIG |  |  |  | DATE | [6 empty] | 2023-01-16
WBS NUMBER | TASK TITLE | START DATE | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
|  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | 2022-12-19 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Project Charter Revisions | 2023-01-16 | 100% | bar: WEEK 2 W
1.2 | Revise Flowchart | 2023-01-16 | 90% | bar: WEEK 2 W to WEEK 3 W
1.3 | Database Structure | 2023-01-16 | 40% | bar: WEEK 2 R to WEEK 3 R
1.4 | Create Repository | 2023-01-16 | 70% | bar: WEEK 3 M to WEEK 3 R
1.5 | Project Initiation | 2023-01-23 | 60% | bar: WEEK 3 T to WEEK 3 R
1.6 | Initial Code | 2023-01-30 | 50% | bar: WEEK 3 F
2 | Menu Function
2.1 | CreateSign-up Record | 2023-02-06 | 22% | bar: WEEK 4 M to WEEK 4 R
2.2 | Create View Record | 2023-02-13 | 16% | bar: WEEK 4 F to WEEK 5 F
2.3 | Create Modify Record (Grades) | 2023-02-20 | 0%
2.4 | Create Modify Record | 2023-02-20
2.5 | Create Delete Record | 2023-02-27
3 | Project Conception and Initiation
3.1 | Testing | 2023-02-27 | 0%
3.2 | Cleaning the code | 2023-02-28 | 0%
3.3.1 | Final Checking | 2023-03-01 | 0%